## Sheet1
Field | Details
Project Name | Bank Funds Transfer
Module | Funds Transfer (Web Application)
Prepared By | QA Intern
Reviewed By | QA Lead
Test Start Date | 2025-06-25
Test End Date | 2025-07-02
Test Environment | Windows 10, Chrome 137+, Android Chrome (Mobile View)
Tools Used | Excel, Jira, Postman, Chrome DevTools
Total Test Scenarios | 12
Total Test Cases Executed | 17
Passed | 14
Failed | 3
Blocked | 0
Pass Rate | 82.35%
Critical Defects | 1 (BUG002 - OTP expiry flaw)
High Severity Defects | 1 (BUG001 - Duplicate beneficiary)
Medium Severity Defects | 1 (BUG003 - Transaction not recorded)
Exit Criteria - 100% test cases executed | Yes
Exit Criteria - Major bugs identified and logged | Yes
Exit Criteria - Critical blockers resolved | No (Pending OTP expiry fix)
Exit Criteria - Reports submitted | Yes
Exit Criteria - Final sign-off | No (Pending verification)
Lessons Learned | Strengthen OTP expiry logic, improve transaction logging, add edge-case coverage
Recommendations | Fix critical bugs, retest failed cases, conduct short regression cycle
Test Closure Statement | System Testing for Bank Funds Transfer completed. All major defects documented. Ready for UAT after critical fixes.