## Sheet1
Field | Details
Project Name | Bank Funds Transfer
Module Name | Funds Transfer
Test Start Date | 2025-06-01
Test End Date | 2025-06-10
Prepared By | QA Intern
Reviewed By | QA Lead
Test Environment | Windows 10 , Android Mobile (Responsive UI)
Tools Used | Excel, Jira
Total Test Scenarios | 12
Total Test Cases | 17
Test Cases Passed | 14
Test Cases Failed | 3
Test Cases Blocked | 0
Test Case Pass Percentage | 82.35%
Total Defects Logged | 3
Defects Fixed During Execution | 0 (all 3 are still open)
Retested Test Cases | 3
Regression Cycles Run | 1
Major Defects | OTP expiry failure, missing transaction logs, duplicate beneficiary allowed
Test Coverage | 100% of core functionalities tested (Login, Transfer, OTP, History, UI)
Risks Identified | OTP expiry mechanism is faulty; History module needs urgent fix
Recommendations | Fix critical bugs before UAT. Improve validation rules and backend logging.
Test Summary Conclusion | Testing completed with 3 open defects. Ready for UAT after patch release.